## Project Plan
Data Scrape and Validation
Action | Date Completed | % Complete | Notes
Understand the Problem
Define objectives | 2024-03-03 | 100% | Captured in presentation slides
Define scope of work | 2024-03-03 | 100% | Captured in presentation slides
Define deliverables | 2024-03-16 | 100% | Captured in project plan
Deliverable: Project overview documentation | 2024-03-16 | 100% | Captured in presentation slides
PDF Scrape Testing
Test Acrobat exort options | 2024-03-05 | 100%
Test python libraries | 2024-03-07 | 100%
Deliverable: Document test results | 2024-03-07 | 100% | Captured in Excel
VBA Macro Development
General Legislative Data
Define requirements | 2024-03-16 | 100%
Write code | 2024-03-17 | 100%
Test macro | 2024-03-17 | 100%
Document code | 2024-03-17 | 100%
Confirmation Data
Define requirements | 2024-03-16 | 100%
Write code | 2024-03-20 | 100%
Test macro | 2024-03-20 | 100%
Document code | 2024-03-20 | 100%
Deliverable: Export General Activity macro | 2024-03-20 | 100% | Available in GitHub
Deliverable: Export Confirmation macro | 2024-03-20 | 100% | Available in GitHub
Deliverable: Update presentation to include macro scope and details | 2024-03-20 | 100%
Data Scrape
Download resumes in PDF format | 2024-03-03 | 100%
Run OCR on PDFs that contain scanned images (98th - 104th Congresses) | 2024-03-07 | 100% | Used batch Scan and OCR in Acrobat Pro
General Legislative Data
Extract table text to CSV | 2024-03-18 | 100% | Used tabula application
Run cleanup macros and manually correct OCR errors | 2024-03-18 | 100% | Used Excel
Confirmation Data
Extract table text to CSV | 2024-03-20 | 100% | Used tabula application
Run cleanup macros and manually correct OCR errors | 2024-03-20 | 100% | Used Excel
Deliverable: Legislative activity and confirmation data in Excel format | 2024-03-20 | 100%
Data Prep
General Legislative Data
Load data | 2024-03-20 | 100%
Validate variable names (column headings) and standardize | 2024-03-20 | 100%
Transpose dataframe (tidy data) | 2024-03-20 | 100%
Merge data to single dataframe | 2024-03-20 | 100%
Update datatypes and formats as needed | 2024-03-20 | 100%
Export to Excel | 2024-03-20 | 100%
Confirmation Data
Load data | 2024-03-20 | 100%
Validate variable names (column headings) and standardize | 2024-03-21 | 100%
Transpose dataframe (tidy data) | 2024-03-22 | 100%
Merge data to single dataframe | 2024-03-22 | 100%
Update datatypes and formats as needed | 2024-03-22 | 100%
Export to Excel | 2024-03-22 | 100%
Deliverable: Legislative activity data tidied and saved to a single Excel file | 2024-03-22 | 100%
Deliverable: Confirmation data tidied and saved to a single Excel file | 2024-03-22 | 100%
Validate Data
Legislative Activity Data
Handle missing data | 2024-03-22 | 100%
Verify data integrity and check for outliers | 2024-03-23 | 100%
Verify totals match detail lines | 2024-03-25 | 100%
Update dataset as needed | 2024-03-25 | 100%
Legislative Activity Data
Handle missing data | 2024-03-25 | 100%
Verify data integrity and check for outliers | 2024-03-25 | 100%
Verify totals match detail lines | 2024-03-27 | 100%
Update dataset as needed | 2024-03-27 | 100%
Deliverable: Final Legislative Activity dataset in Excel format | 2024-03-27 | 100% | Available in GitHub
Deliverable: Final Confirmation dataset in Excel format | 2024-03-27 | 100% | Available in GitHub
Deliverable: Document data issues and updates in final presentation | 2024-03-27 | 100% | Available in GitHub
Project Closeout
Check-in all final code and documentations | 2024-03-29 | 100% | Available in GitHub
Publish project assets and findings as appropriate | 2024-03-29 | 100% | Available in GitHub

## Analysis Checklist
Metric / Report / Graph | Status

## Issue Log
Issue | Issue Type | Date Entered | Date Resolved | Status | Resolution

## Data Cleanup Log
Issue | Issue Type | Date Entered | Status | Resolution