## Project Plan
Data Scrape and Validation |  | Project plan based on CRISP-DM Methodology, as described by Northeastern University
https://graduate.northeastern.edu/resources/data-analysis-project-lifecycle/
Action | Start Date | Target Date | Date Completed | % Complete | Notes
Understand the Problem
Define objectives |  |  | 2024-03-03 | 100% | Captured in presentation slides
Define scope of work |  |  | 2024-03-03 | 100% | Captured in presentation slides
Define deliverables |  |  |  | 25% | Captured in project plan
Deliverable: Project overview documentation
PDF Scrape Testing
Test Acrobate exort options |  |  | 2024-03-05 | 100%
Test python libraries |  |  | 2024-03-07 | 100%
Deliverable: Document test results |  |  | 2024-03-07 | 100% | Captured in Excel
Data Scrape
Download resumes in PDF format |  |  | 2024-03-03 | 100%
Run OCR on PDFs that contain scanned images (98th - 104th Congresses) |  |  | 2024-03-07 | 100% | Used batch Scan and OCR in Acrobat Pro
Extract table data |  |  |  | 5% | Used Tabula app
Data Prep
General Legislative Data
Review and update table data as needed |  |  |  | 5%
Create Macro
Document Macro
Load data
Validate variable names (column headings)
Update datatypes and formats as needed
Tidy data |  |  | 2024-02-19 | 100%
Preview data |  |  | 2024-02-19 | 100%
Delete NaN rows and columns |  |  | 2024-02-19 | 100%
Identify and describe variables |  |  | 2024-02-19 | 100%
Rename variables for clarity |  |  | 2024-02-19 | 100%
Update datatypes and formats as needed |  |  | 2024-02-21 | 100%
Preview data |  |  | 2024-02-22 | 100%
Confirmation activity data: |  |  | 2024-02-22 | 100% | DataPrepConfirmations.ipynb
Collect data |  |  | 2024-02-22 | 100%
Load data |  |  | 2024-02-22 | 100%
Consolidate data |  |  | 2024-02-22 | 100%
Tidy data |  |  | 2024-02-22 | 100%
Preview data |  |  | 2024-02-22 | 100%
Delete NaN rows and columns |  |  | 2024-02-22 | 100%
Identify and describe variables |  |  | 2024-02-22 | 100%
Rename variables for clarity |  |  | 2024-02-22 | 100%
Update datatypes and formats as needed |  |  | 2024-02-22 | 100%
Membership demographics data:
Collect data |  |  | 2024-02-22 | 100% | DataPrepDemographics.ipynb
Load and tidy party data |  |  | 2024-02-26 | 100%
Load and tidy seniority data |  |  | 2024-02-26 | 100%
Load and tidy sex data |  |  | 2024-02-27 | 100%
Load and tidy race data |  |  | 2024-02-27 | 100%
Load and tidy occupation data |  |  | 2024-02-27 | 100%
Load and tidy religion data |  |  | 2024-02-27 | 100%
Consolidate data |  |  | 2024-02-28 | 100%
Deliverable: Document data source(s) |  |  | 2024-02-28 | 100% | Captured in presentation slides
Deliverable: Source control project setup |  |  | 2024-02-28 | 100% | github.com/tamimcm416/congressional_activity/
Deliverable: Update presentation |  |  | 2024-03-01 | 100%
Validate Data
Create lookup table for code descriptions
Handle missing data
Remove duplicate data
Look for and cleanup miscoded data
Verify data integrity and check for outliers
Remove irrelevant variables
Save to CSV
Deliverable: Published dataset ready for EDA
Deliverable: Documentation of work completed and findings
Exploratory Data Analysis
Statistical analysis
Exploratory Data Analysis
Number of injuries
Type and severity of injuries
Patient demographics
Products involved
Hospital characteristics
Data Visualizations
Deliverable: Checklist of questions to be explored
Deliverable: Documentation of work completed and findings
Validation and QA
Review findings
Validate process
Validate data
Deliverable: Documentation of work completed and findings
Deliverable: Review objectives - is more work needed?
Visualization and Presentation
Review all past deliverables for clarity and consistency
Craft a compelling story
Document recommendations
Deliverable: Final visualizations
Deliverable: Final presentation
Project Closeout
Check-in all final code and documentations
Publish project assets and findings as appropriate
Data Collection
NEIS data downloads | 2024-01-19 | 2024-01-19 | 2024-01-19 | 100% | Excel files from 2013 - 2022
Load injury data to Azure SQL | 2024-01-19 | 2024-01-19 | 2024-01-19 | 100% | Database name = ProductInjury
Data Preparation
Validate (and correct) consistency of variables names | 2024-01-19 | 2024-01-19 | 2024-01-19 | 100% | Validated Manually in MSSM
Validate (and correct) consistency of codes / labels | 2024-01-19 | 2024-01-19 | 2024-01-24 | 100% | Python Notebook - DataPrepCodes
Load scrubbed codes and labels to Azure SQL | 2024-01-19 | 2024-01-19 | 2024-01-28 | 100% | Imported using MSSM
Validate and merge injury datasets | 2024-01-28 | 2024-01-28 |  | 50% | Python Notebook - DataPrepInjuries
Load injury data to Azure SQL |  |  |  |  | Python Notebook - DataPrepInjuries
Data Analysis
Number of products tracked
Distribution of injuries by product
Findings / Presentation
Review DataPrepCodes notebook
Project Close Out

## Analysis Checklist
Metric / Report / Graph | Status

## Issue Log
Issue | Issue Type | Date Entered | Date Resolved | Status | Resolution

## Data Cleanup Log
Issue | Issue Type | Date Entered | Status | Resolution