## Project Plan
Data Scrape and Validation
Action | Date Completed | % Complete | Notes
Understand the Problem
Define objectives | 2024-03-03 | 100% | Captured in presentation slides
Define scope of work | 2024-03-03 | 100% | Captured in presentation slides
Define deliverables | 2024-03-16 | 100% | Captured in project plan
Deliverable: Project overview documentation | 2024-03-16 | 100% | Captured in presentation slides
PDF Scrape Testing
Test Acrobat exort options | 2024-03-05 | 100%
Test python libraries | 2024-03-07 | 100%
Deliverable: Document test results | 2024-03-07 | 100% | Captured in Excel
VBA Macro Development
General Legislative Data
Define requirements | 2024-03-16 | 100%
Write code | 2024-03-17 | 100%
Test macro | 2024-03-17 | 100%
Document code | 2024-03-17 | 100%
Confirmation Data
Define requirements | 2024-03-16 | 100%
Write code |  | 60%
Test macro |  | 60%
Document code
Deliverable: Export General Activity macro
Deliverable: Export Confirmation macro
Deliverable: Update presentation to include macro scope and details
Data Scrape
Download resumes in PDF format | 2024-03-03 | 100%
Run OCR on PDFs that contain scanned images (98th - 104th Congresses) | 2024-03-07 | 100% | Used batch Scan and OCR in Acrobat Pro
General Legislative Data
Extract table text to CSV | 2024-03-18 | 100% | Used tabula application
Run cleanup macros and manually correct OCR errors | 2024-03-18 | 100% | Used Excel
Confirmation Data
Extract table text to CSV |  |  | Used tabula application
Run cleanup macros and manually correct OCR errors |  |  | Used Excel
Deliverable: Legislative activity and confirmation data in Excel format
Data Prep
General Legislative Data
Load data
Validate variable names (column headings) and standardize
Transpose dataframe (tidy data)
Merge data to single dataframe
Update datatypes and formats as needed
Export to Excel
Confirmation Data
Load data
Validate variable names (column headings) and standardize
Transpose dataframe (tidy data)
Merge data to single dataframe
Update datatypes and formats as needed
Export to Excel
Deliverable: Legislative activity data tidied and saved to a single Excel file
Deliverable: Confirmation data tidied and saved to a single Excel file
Validate Data
Legislative Activity Data
Handle missing data
Verify totals match detail lines
Verify data integrity and check for outliers
Update data and export to Excel as final dataset
Legislative Activity Data
Handle missing data
Verify totals match detail lines
Verify data integrity and check for outliers
Update data and export to Excel as final dataset
Deliverable: Final Legislative Activity dataset in Excel format
Deliverable: Final Confirmation dataset in Excel format
Deliverable: Document data issues and updates in final presentation
Project Closeout
Check-in all final code and documentations
Publish project assets and findings as appropriate

## Analysis Checklist
Metric / Report / Graph | Status

## Issue Log
Issue | Issue Type | Date Entered | Date Resolved | Status | Resolution

## Data Cleanup Log
Issue | Issue Type | Date Entered | Status | Resolution